## Action Plan
Plan of Action 2020
Implementing Agency: National Science and Technology Commission
| Responsible person and Contact no : |  | Dr. Thamara F. Dias (Acting Director) 0112186711
Implementing Agency: National Science and Technology Commission (NASTEC)
| Programme / Project : | Activity/Sub Activity | Total Allocation 2020 (Rs.mn) | Date of Commence | Date of Completion | Financial Target |  |  | Physical Target |  |  | Output or Indicator\KPI | Related Policies | Remarks
Object Code | [5 empty] | Jan - Apr | May-Aug | Sep - Dec | Jan - Apr | May-Aug | Sep - Dec
2201 | Projects & Programmes aligned with රට හදන සෞභාග්‍යයේ දැක්ම | Smart Agriculture Projects & Programmes | 8.5 | 2020-01-01 | 31/12/2020 | 0.75 | 3.9 | 3.85 | Situational analysis and Stakeholder consultation of identified projects in 6 sectors | 50% Implementation of identified projects by responsible agencies | 50% Implementation of identified projects by responsible agencies | Number of Stakeholder consultation meetings held | National Policy Framework (NPF) | *For details please refer Annexure 01 & Annexure 02
Health sector Projects & Programmes
|  | Environment sector Projects & Programmes | [9 empty] | Number of Projects & Programmes implemented in 6 sectors*
Energy sector Projects & Programmes
Natural Resources Projects & Programmes
Projects & Programmes related to People-centric Economy
2201 | Establishment of system to Advice Government on STI | Initiate working groups consisting of Senior Scientists, Young Scientists and Scientists from other professional bodies | 1.5 | 2020-01-01 | 31/12/2020 | 0.6 | 0.4 | 0.5 | Science advice working group meetings | Science advice working group meetings | Science advice working group meetings | Number of working group meetings held | National S&T Policy, NRDF, National Policy Framework (NPF)
|  | Young scientists forum (YSF) activities on science advice | [6 empty] | YSF Meeting /Activities | YSF Meetings /Activities | YSF Meetings /Activities | YSF Meetings /Activities Held
|  | 9th YSF Research Symposium | [6 empty] | 9th YSF Research Symposium |  |  | 9th YSF research symposium held
2201 | Development of S&T Related Policies, Strategies and Plans | Development of National STI Strategy/ NRDF Implementation Strategy | 5.4 | 2020-01-01 | 31/12/2020 | 0.3 | 2.7 | 2.4 | Draft National Research and Development Framework (NRDF) Implementation Strategy development based on Survey | Technical Committee Meeting and Finalize the NRDF Implementing Strategy in Digital platform | Technical Committee Meting Finalized / Monitoring and evaluation of NRDF Strategy in Digital platform | National STI/NRDF Strategy in Digital Platform 2020-2023 | National S&T Policy, NRDF, National Policy Framework (NPF)
|  | Development of S&T related New Policies/NRDF Strategy | [6 empty] | Appointing of working group based on Policy Development related STI Policies/Strategy | Preparation 1st Draft based on the concept paper of working committee on identified STI Policy/ Strategy | Conducting a Stakeholders meeting/Public awareness/ M &E on Finalized the Draft of STI Policy / Strategy | STI Policy / Strategy 2020 - 2023
|  | International collaboration related to S&T activities | [6 empty] | STEPI/NAM activities | STEPI/NAM activities | STEPI/NAM activities | STEPI/NAM programmes & workshops held
2201 | Review of S&T institutions | Review of 07 S&T Institutions | 3.5 | 2020-01-01 | 31/12/2020 | 0.5 | 1 | 2 | Review of S&T Institutions | Review of S&T Institutions | Review of S&T Institutions | % completion of institution reviews | National S&T Policy, NRDF, National Policy Framework (NPF)
2201 | Assessment of S&T Status of Sri Lanka | Data collection | 3.5 | 2020-01-01 | 31/12/2020 | 0.05 | 0.45 | 3 | 50% Completion of data collection | Completion of data collection | completion of Analysis of Data | Report on STI Status of Sri Lanka | National S&T Policy, NRDF, National Policy Framework (NPF)
|  | Data Analysis | [6 empty] | Preparation of working plan for data analysis | 50 % completion of Analysis of Data | Completion of report writing
|  | Report Writing | [7 empty] | Identify and appoint editorial Panel
Report Publishing & Dissemination
2201 | Pre BICOST IX Activities - 9th Sri Lanka Biennial Conference on Science & Technology (BICOST IX) in 2020 | BICOST IX - 2020 | 4 | 2020-01-01 | 31/12/2020 | 0.1 | 0.4 | 3.5 |  | Pre-BICOST IX - 2020 activities | Organizing and holding the BICOST IX - 2020 | BICOST IX - 2020 held | National S&T Policy, NRDF, National Policy Framework (NPF)
Concurrence of the BICOST Theme in aligned with Pre BICOST Activities 2020
2201 | Capacity Building - Staff Training | Capacity Building - Staff Training | 0.7 | 2020-01-01 | 31/12/2020 |  | 0.3 | 0.4 |  |  |  | No of person days trained
2201 | Acquisition of Fixed Assets | WEB Software Development | 2 | 2020-01-01 | 31/01/2020 | 1.3 | 0.7 |  |  |  |  | Complete as per the Procurement Plan
Server computer
| Total |  | 29.1 |  |  | 3.6 | 9.85 | 15.65