## Smart Agriculture
Annexure 02
Projects & Programmes aligned with රට හදන සෞභාග්‍යයේ දැක්ම
Implementing Agency : National Science and Technology commission
Smart Agriculture
| Activity | Jan | Feb | Mar | Apr | May | Jun | Outcome (6 month) | July | Aug | Sep | Oct | Nov | Dec | Outcome (12 month)
1 | Initiate production of bio-fertilizer by local farmers
a) | Initial planning | [6 empty] | *Discussion meetings with relavent parties (Feasibility Study) *Farmer awareness programs to use biofertilizer instead of chemical fertilizer | [6 empty] | *Production of bio fertilizers (i.e. compost, slow releasing bio-fertilizers) and distribute to farmers at low cost
b) | Expert committee discussions
c) | Stakeholder consultations
d) | Implementation of actions
e) | Follow ups
2 | Introduce Nano-fertilizer technolgy to farmers at low cost
a) | Initial planning | [6 empty] | *Situational Analysis of the status of production of Nano fertilizer *Farmer awareness programs on using nano fertilizer | [6 empty] | *Production of nano fertilizers and distribute to farmers at low cost
b) | Expert committee discussions
c) | Stakeholder consultations
d) | Implementation of actions
e) | Follow ups
3 | Local manufacture of high tech drones
a) | Initial planning | [6 empty] | *Discussion meetings (held with ACCIMT for local production of drones in commercial scale) | [6 empty] | *Drone technology used for fertilizer distribution introduced to selected farming lands
b) | Expert committee discussions
c) | Stakeholder consultations
d) | Implementation of actions
e) | Follow ups
4 | Promote Precision Agriculture Practices using drone technology
a) | Initial planning | [6 empty] | *Discussion meetings (held with DoA and ACCIMT for introducing drone technolgy to be used for pest, disease, weed detection to Sri Lankan farmers) | [6 empty] | *Drone technology used for pest, disease, weed detection in selected farming lands and apply pesticides & weedicides only to effected areas *Drone technology used to gather data in selected farming lands and predict yeild
b) | Expert committee discussions
c) | Stakeholder consultations
d) | Implementation of actions
e) | Follow ups
5 | Initialize Seed Research Programme upgraded with cutting edge science of seed technology
a) | Initial planning | [6 empty] | *Stakeholders meetings to evaluate the status of seed research and seed production | [6 empty] | *production of high quality low cost seeds
b) | Expert committee discussions
c) | Stakeholder consultations
d) | Implementation of actions
e) | Follow ups
6 | Facilitate small scale local seed production entrepreneurs
a) | Initial planning | [6 empty] | Provide loan facilities for small scale local seed production entrepreneurs | [6 empty] | 10 Number of small scale seed production entrepreneurs developed
b) | Expert committee discussions
c) | Stakeholder consultations
d) | Implementation of actions
e) | Follow ups
7 | Collaboration with private sector to produce good quality seeds
a) | Initial planning | [6 empty] | Discussion Meetings (with Farmers for small scale seed production and private companies such as CIC, Hayleys for large scale seed production | [6 empty] | commercial production of high quality seeds that farmers can buy at low cost
b) | Expert committee discussions
c) | Stakeholder consultations
d) | Implementation of actions
e) | Follow ups
8 | Develop new technological methods to add value to spices such as cinnamon, pepper, cloves, nutmeg, mace, ginger, turmeric, citronella, cardamom, lemon grass, etc.
a) | Initial planning | [6 empty] | Meetings with relevant stakeholders Research grants given to ITI, DEA researchers to start research on value addition to spices | [6 empty] | Commercialize 10 new value added spice products developed through research by ITI, and Department of Export Agriculture
b) | Expert committee discussions
c) | Stakeholder consultations
d) | Implementation of actions
e) | Follow ups
9 | Develop new research and technological methods to develop value added products of tea, coconut, rubber
a) | Initial planning | [6 empty] | 2) Discussion Meetings with CRI, TRI, RRI 2) research grants given for coconut, tea, rubber value addition research by CRI, TRI, RRI | [6 empty] | 1)Coconut plucking macines developed with Coconut Research Institute & SL Inventors Commission that are of low cost 2) Distribute high yeid tea, rubber, coconut varieties produced through research for local farmers
b) | Expert committee discussions
c) | Stakeholder consultations
d) | Implementation of actions
e) | Follow ups
10 | Provide technology, low interest loans, marketing facility for productions to facilitate startups for Small & Medium Scale Agriculture Enterprises
a) | Initial planning | [6 empty] | 1) Select suitable Small & Medium Scale Agriculture Enterprises for statups and have discussions with them 2) Provide marketing facility to selected SMEs through social media | [6 empty] | Technology, low interest loans given to selected Small and Medium Scale Agriculture Enterprises (SMEs) by Institute of Agrotechnology & Rural Science. Together with Ministry of Industries.
b) | Expert committee discussions
c) | Stakeholder consultations
d) | Implementation of actions
e) | Follow ups

## Health
Projects & Programmes aligned with රට හදන සෞභාග්‍යයේ දැක්ම
Implementing Agency : National Science and Technology commission
Health Sector
| Activity | Jan | Feb | Mar | Apr | May | Jun | Outcome (6 month) | July | Aug | Sep | Oct | Nov | Dec | Outcome (12 month)
1 | Facilitate to provide buyback Agreement of Anitivenom
a) | Initial planning | [6 empty] | *Held meetings with Ministry of Health,Research team,National Medicinal Regulatory Agency (NMRA) and other relavant Authorities ( 3 Nos.) *Producing Saftey profile of the Product to NMRA *Obtaining the Money- back agreement for the Product from the Ministry of Health | [6 empty] | *Startup the construction of the manufacturing Plant
b) | Expert committee discussions
c) | Stakeholder consultations
d) | Implementation of actions
e) | Follow ups
2 | Facilitate to provide Grants to resaerch team to initiate other local vaccine production in the same plant.
a) | Initial planning | [6 empty] | *Discussion meetings held (02 Nos.) with NRC,Universities to identify the potential research teams *Identify a research team in the field of Developing Kaneru (Yellow Oleander) and Colchicine antibodies to treat poisoned Patients at Government Hospitals | [6 empty] | *Align the identified team to work with the UOP - Antivenom project team *Get approval for a Grant to a identified team to initiate a research work on Kaneru antibody development (01 No.)
b) | Expert committee discussions
c) | Stakeholder consultations
d) | Implementation of actions
e) | Follow ups
3 | Updating Ayurveda Pharmacopoeia-Establish National Aayurveda Pharmacopoeia Commission/Facilitate to provide the allocated funding for the project
a) | Initial planning | [6 empty] | *Meetings held with National Ayurveda Pharmacopoeia Development Committee (02 Nos.) *Appointing a Steering Committee *Establish National Ayurveda Pharmacopoeia Commission *Facilitate to make available the allocated funding for the Project proposal submitted to Ministry of Health and Indigenious Medicine by the Committee | [6 empty] | *Rectifying exsisting Ayurveda Pharmacopoeia
b) | Expert committee discussions
c) | Stakeholder consultations
d) | Implementation of actions
e) | Follow ups
4 | Local Quality Control (QC) testing of Imporated Pharmaceuticals-Provide accreditation for local drug testing labs/Facilitate Provide Grants for Bioequivalance and Biowaiver studies
a) | Initial planning | [6 empty] | *Discussion meetings held with the key players ( 03 Nos.) *Submission of the propsal to Ministry of Higher Education, Innovation & Technology * Proposal submission to NSF/NRC | [6 empty] | *Make available to function an accrediated QC lab at University of Colombo *Get funding approval to initiate a Bioequivalance study at University of Colombo (01 No.)
b) | Expert committee discussions
c) | Stakeholder consultations
d) | Implementation of actions
e) | Follow ups
5 | Promote research on cutting edge medical technologies-Provide Provision to Universities and S & T institutes to enhance the research Capacity on AI,Nanotechnology,Robotics in Medicine (Precision Medicine)
a) | Initial planning | [6 empty] | *Discussion meetings held with Committees and the key players ( 02 Nos.) * Identify a Research Team/ Academic to provide a Grant support for Research to be done in the Fields | [6 empty] | *Get funding approval to the identified academic team to proceed the research work in the particular area ( 01 No.)
b) | Expert committee discussions
c) | Stakeholder consultations
d) | Implementation of actions
e) | Follow ups
6 | Commercialization of high tech medical products-Provide startup & marketing provisions for high tech medical products developed through Research
a) | Initial planning | [6 empty] | *Discussion meetings held with Committees and the key players (02 Nos.), *Identify a research Team/Acadmic to Support the Funding for Commercialize the Product/Technology | [6 empty] | * Get Funding approval for an identified Research Team/Academic to commercialize the tech/Product (01 No.)
b) | Expert committee discussions
c) | Stakeholder consultations
d) | Implementation of actions
e) | Follow ups
7 | Cancer Prevention-Promote healthy meals,Production of Organic foods ,Promote proper eating habits at all ages
a) | Initial planning | [6 empty] | *Discussion meetings held with Committees,University Research Teams (UOC,UOSJ,UOP,UOK ), Minstry of Education and Other Key players *Workshop and Awarness programme Conducted on promoting healthy meals/ Proper eating habits ( 03 Nos.),Awarness programme conducted on promoting the production of Organic foods to farmers (1 No.) | [6 empty] | *Perventing the Cancer through the awraness programes on Healthy meals for School Childrean / Teachers/Farmers
b) | Expert committee discussions
c) | Stakeholder consultations
d) | Implementation of actions
e) | Follow ups

## Environment
Projects & Programmes aligned with රට හදන සෞභාග්‍යයේ දැක්ම
Implementing Agency : National Science and Technology commission
Environment
| Activity | Jan | Feb | Mar | Apr | May | Jun | Outcome ( 6 Month) | July | Aug | Sep | Oct | Nov | Dec | Outcome (12 month)
1 | Introduce novel waste management system and public awareness through digitized applications
a) | Initial planning | [6 empty] | *Stream line the identified household compost production projects and overview the current status | [6 empty] | Implement Sustainable waste Management system at 3 Local Government bodies
b) | Expert committee discussions
c) | Evaluation of ongoing projects
d) | Implementation of pilot studies
e) | Follow ups
2 | Introduce Eppawala phosphate as a phosphate fertilizer for suitable annual crops
a) | Initial planning | [6 empty] | * Meetings with relevant authorities and the stakeholders (SLINTEC/NIFS) *Identify the barriers encounterd in R&D activities on Eppawala Phosphate to produce the Ferilizer * Submit an expert evaluation report in the subject | [6 empty] | Startup the production of Low Cost Phosphate Fertilizers (Pilot Project)
b) | Expert committee discussions
c) | Stakeholder consultations
d) | Implementation of actions
e) | Follow ups

## Energy
Projects & Programmes aligned with රට හදන සෞභාග්‍යයේ දැක්ම
Implementing Agency : National Science and Technology commission
Energy
| Activity | Jan | Feb | Mar | Apr | May | Jun | Outcome (6 month) | July | Aug | Sep | Oct | Nov | Dec | Outcome (12 month)
1 | Establish solar panels system in the universities encouraging R&D activities in relation to solar energy
a) | Initial planning | [6 empty] | *Establishment of Solar power energy System at Wayamba University (Pilot Project) | [6 empty] | *Extending the project to University of Jaffna,Rajarata and Uwa Wellessa
b) | Expert committee discussions
c) | Stakeholder consultations
d) | Implementation of actions
e) | Follow ups
2 | Development of Super Capacitors/Development of Improved Batteries
a) | Initial planning | [6 empty] | *Discussion meetings with Relavant authorities* Develop super capacitors (prototype) to be used in the manifacture of Automobile electric batteries (Feasible study) | [6 empty] | *Develop Imrpoved (effcient) super capacitors to use in electric Automobile industry
b) | Expert committee discussions
c) | Stakeholder consultations
d) | Implementation of actions
e) | Follow ups
3 | Development of consumer friendly Smart Meters (Electricity / Water)
a) | Initial planning | [6 empty] | * Meetings with relavant researchers , Acdemics , Industries and Other stakeholders/ Committees ( 4 Nos.) *Submit an Evaluation Report on Ongoing Research activities in the field. | [6 empty] | *Development of Consumer friendly Smart Meters (Pilot study -Prototype)
b) | Expert committee discussions
c) | Stakeholder consultations
d) | Implementation of actions
e) | Follow ups

## Natural Resources
Projects & Programmes aligned with රට හදන සෞභාග්‍යයේ දැක්ම
Implementing Agency : National Science and Technology commission
Natural Resources
| Activity | Jan | Feb | Mar | Apr | May | Jun | Outcome (6 month) | July | Aug | Sep | Oct | Nov | Dec | Outcome (12 month)
1 | Finalize the National Policy on Mineral Resources
a) | Expert committee discussions | [6 empty] | *Conclude the Technical Meeting for Finalizing the Policy * Joint Cabinet paper submission by MOHTI and MEAE | [6 empty] | * Mobilize the Implementing strategy and action plan * Follow up the activity by M&E
b) | Stakeholder consultations
c) | Implementation of actions
d) | Follow ups
2 | Converting graphite into graphene and other value added material (value additon convertion 500 - 3000%)
a) | Initial planning | [6 empty] | *Technology difusion to the industry and commersilization | [6 empty] | *Value added Graphite to be exported
b) | Expert committee discussions
c) | Stakeholder consultations
d) | Implementation of actions
e) | Follow ups
3 | Introduce novel value addition techniques for low grade Gems and other minerals
a) | Initial planning | [6 empty] | *Expert meeting held and stream line the technology and product development | [6 empty] | * Value added Gems and other Minerals to be exported
b) | Expert committee discussions
c) | Stakeholder consultations
d) | Implementation of actions
e) | Follow ups
4 | Introduce Zero-waste policy in conjunction with value addition by Environment friendly mining techniques in best standard parctices
a) | Expert committee discussions | [6 empty] | *Approced by Mineral Policy approval by Cabinet | [6 empty] | *Mineral Policy Implemented
b) | Stakeholder consultations
c) | Implementation of actions
d) | Follow ups
5 | Use high-tech innovation with adequate mesuares on mineral exploring, mapping, assessing on opt value added product
a) | Initial planning | [6 empty] | *Meeting held with relevant Experts and Institutions | [6 empty] | *Develeoped Technology to be accesesd in all Mineral Sectors in both Public and Privat Indsutry
b) | Expert committee discussions
c) | Stakeholder consultations
d) | Implementation of actions
e) | Follow ups

## People Centric Economy
Annexure 01
Projects & Programmes aligned with රට හදන සෞභාග්‍යයේ දැක්ම
Implementing Agency : National Science and Technology commission
Peoples Centric Economy
| Activity | Jan | Feb | Mar | Apr | May | Jun | Outcome (6 month) | July | Aug | Sep | Oct | Nov | Dec | Outcome (12 month)
1 | Provide technical oppertunities and knowladge on starts up and long run Business models
a) | Initial planning | [6 empty] | *Discussion and Meeting held with UGC and UOC | [6 empty] | * On line degree programms established in enabling strats up and Entrepreneur developed
b) | Expert committee discussions
c) | Stakeholder consultations
d) | Implementation of actions
e) | Follow ups
2 | Knowladge enrichment and encourage value addition
a) | Initial planning | [6 empty] | * Discussions and Meeting held in relevant stakholders | [6 empty] | * Established and Mobilized the value chain Businesses and Starts up
b) | Expert committee discussions
c) | Stakeholder consultations
d) | Implementation of actions
e) | Follow ups
3 | Introduce a legal framwork for the provision of interest free loan schem for graduate
a) | Initial planning | [6 empty] | *Discussion and Meeting held with relevant parties and Feasibility Study held | [6 empty] | *Mobilized the funds upon the subjected to the legal framework
b) | Expert committee discussions
c) | Stakeholder consultations
d) | Implementation of actions
e) | Follow ups
4 | Provide all kind of facilities including land, credit and infrastucture etc. needed to grow up the local entrepreneur securely
a) | Initial planning | [6 empty] | *Discussion and Meeting held with relevant parties and Feasibility Study held | [6 empty] | *Established the value chain creations and Innovation ecosystem
b) | Expert committee discussions
c) | Stakeholder consultations
d) | Implementation of actions
e) | Follow ups
5 | clear set of objectives in PPP by Protect, secure and strengthen the local Entrepreneurs
a) | Initial planning | [6 empty] | *Discussion and Meeting held with relevant parties and Feasibility Study held | [6 empty] | * Established and Mobilized the value chain Businesses and Starts up
b) | Expert committee discussions
c) | Stakeholder consultations
d) | Implementation of actions
e) | Follow ups
6 | Introduce or Revisit Acts and regulations in conjuction with innovation value chain and IPR where hinderd the progress and performances
a) | Initial planning | [6 empty] | *Discussion and Meeting held with relevant parties and Feasibility Study held | [6 empty] | * Established and Mobilized the value chain Businesses and Starts up
b) | Expert committee discussions
c) | Stakeholder consultations
d) | Implementation of actions
e) | Follow ups
7 | Analyse tech. landscape in industries and promote infusion of high-tech product, process and servise
a) | Initial planning | [6 empty] | *Discussion and Meeting with stakhodered held | [6 empty] | * Established and Mobilized the value chain Businesses and Starts up
b) | Expert committee discussions
c) | Stakeholder consultations
d) | Implementation of actions
e) | Follow ups
8 | Establish technology and market information network including database as readty to serve to industry and promote to diffise through starts up and SME
a) | Initial planning | [6 empty] | *Discussion and Meeting with stakhodered held | [6 empty] | *Market Survey Information data base established
b) | Expert committee discussions
c) | Stakeholder consultations
d) | Implementation of actions
e) | Follow ups